## Maintenance PSURs
MDR Certificate | TD | PSUR/PMSR ID | Product Name | Class | Type | Start Period | End Period | Frequency | Due Date | Status | Writer | Combined PSUR | Notes | Days Remaining | Priority | Quarter | Completion % | Overdue?
TBD | TD002 | PMS002R | Leisegang Coloscopes | I | Medical Device | 2021-01-01 | 2025-12-31 | 3 years | 2026-04-01 | In progress | Terence | None | none | -5 | 🟠 URGENT | Q2 2026 | 50 | ⚠️ YES
TBD | TD003 | PMS003R | Ally Uterine Positioning System | I | Medical Device | 2023-01-01 | 2025-12-31 | 3 years | 2026-01-15 | In Review | Terence | None | Determining the denominator | N/A | ⚪ TBD | TBD | 0 | No
TBD | TBD | PSUR007 | LoneStar Retractor Kit | IIa | Medical Device | 2023-01-01 | 2024-12-31 | 2 years | 2026-02-20 | In progress | TBD | None |  | -45 | 🔴 OVERDUE | Q1 2026 | 50 | ⚠️ YES
TBD | TD007 | PMS007R | Retractors | Is | Medical Device | TBD | TBD |  |  | Not Started | TBD | Combine with PSUR007 |  | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD008 | PMS008R | Endosee Hysteroscopy Product Family | I | Medical Device | 2021-01-28 | 2025-05-30 | 3 years | 2026-03-01 | Completed | Terence | None |  | - | ✅ DONE | TBD | 100 | No
TBD | TD009 | PMS009R | Comfit Trake - Nofit, NEO-prep | I | Medical Device | 2020-05-01 | 2025-12-31 | 3 years |  | In Review | Terence |  |  | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD062 | PMS062R | Endometrial_Suction_Curette | I | TBD |  |  | TBD | Immediate | Not Started | TBD | None | No available documents released in MC | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD123 | PMS123R | K-Systems Flex Short-term Incubator Module | I | Fertility | 2021-12-31 | 2027-12-30 | 3 years |  | Not Started | TBD | None | Terence will be conforming | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD124 | PMS124R | Embryo Biopsy Kit | I | Medical Device | 2021-12-31 | 2027-12-30 | 3 years |  | Not Started | TBD | None | Terence will be conforming | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD125 | PMS125R | Endometrial Biopsy Kit | I | Medical Device | 2022-12-31 | 2028-12-30 | 3 years |  | Not Started | TBD | None | Terence will be conforming | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD017 | PMSR017 | EZ-Grip & Comfort Rest | I | Fertility | 2021-01-01 | 2026-01-14 | 3 years | 2026-01-23 | In Review | Terence | None | Need to check with Terence | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD018 | PSUR018 | LEEP ELECTRODES | IIb | Medical Device | 2025-06-01 | 2026-05-31 | 1 year | 2026-09-25 | Not Started | TBD | None |  | 172 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD039 | PSUR039 | Acidified Tyrodes Solution (1060) | III | Media | 2024-07-01 | 2025-06-30 | 1 year | 2026-03-31 | In progress | Harish | None | none | -6 | 🟠 URGENT | Q1 2026 | 50 | ⚠️ YES
MDR 768070 | TD041 | PSUR041 | Liquid Paraffin - CHANGE CURRENT REV C TO B AND B TO A | IIa | Media | 2024-01-01 | 2025-12-31 | 2 years | 2026-05-15 | Not Started | Jeff | Combine in PSUR041 | PSUR041, PSUR205, PSUR301, PSUR302 and PSUR303 are combined in PSUR041 | 39 | 🟡 SOON | Q2 2026 | 0 | No
MDR 768070 | TD044 | PSUR044 | VitriFit™ | IIa | Media | 2024-01-01 | 2025-12-31 | 2 years | 2026-05-08 | Not Started | Jeff | None | none | 32 | 🟡 SOON | Q2 2026 | 0 | No
TBD | TD049 | PSUR049 | Saturn 5 Laser System | IIb | Fertility | 2024-01-01 | 2025-12-31 | 1 year | 2026-03-13 | Not Started | Venkata | None | CER deadline 02 March 2026 | -24 | 🔴 OVERDUE | Q1 2026 | 0 | ⚠️ YES
TBD | TD050 | PSUR050 | RI Witness EHP | IIa | Fertility | 2022-03-01 | 2025-05-31 | 2 years | 2026-02-27 | In Review | Jeff | None | In draft, need to release 3-6-26 Awaiting Sales/complaint data, updating to new template | -38 | 🔴 OVERDUE | Q1 2026 | 0 | ⚠️ YES
TBD | TD070 | PSUR070 | Medical Heatpacks | IIa | Medical Device | 2023-07-01 | 2025-06-30 | 2 years | 2026-02-27 | In progress | Venkata | None | none | -38 | 🔴 OVERDUE | Q1 2026 | 50 | ⚠️ YES
MDR 768179 | TD047 | PSUR047 | SynVitro® Hyadase | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-07-30 | Not Started | TBD | None | none | 115 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD048 | PSUR048 | Integra 3 Micromanipulator | IIa | Fertility | 2024-07-01 | 2026-06-30 | 2 years | 2026-07-30 | Not Started | TBD | None |  | 115 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD071 | PSUR071 | Mobius Elastic Retractors | IIa | TBD | 2023-05-01 | 2025-04-30 | 2 years | 2026-03-13 | In progress | Jeff | None | Sales data request issued 3-24-26 | -24 | 🔴 OVERDUE | Q1 2026 | 50 | ⚠️ YES
TBD | TD051 | PSUR051 | EZ-Range Pipettes | IIb | Fertility | 2024-03-01 | 2026-02-28 | 1 year | 2026-05-22 | Not Started | Venkata | None | none | 46 | 🟡 SOON | Q2 2026 | 0 | No
TBD | TD077 | PSUR077 | Wallace Oocyte Recovery/Collection Sets | IIa | Medical Device | 2022-04-01 | 2025-03-31 | 2 years | 2026-02-20 | In progress | Venkata | None | Routing in MC | -45 | 🔴 OVERDUE | Q1 2026 | 50 | ⚠️ YES
TBD | TD058 | PSUR058 | Apple-Hunt Trocars | IIa | TBD | 2024-04-01 | 2026-03-31 | 2 years | 2026-06-13 | Not Started | Jeff | None | none | 68 | 🟢 ON TRACK | Q2 2026 | 0 | No
TBD | TD060 | PSUR060 | Carter-Thomason Port Closure Products | IIa | TBD | 2024-08-01 | 2026-07-31 | 2 years | 2026-08-28 | Not Started | TBD | None | none | 144 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD081 | PSUR081 | Fischer cone Biopsy Electrodes | IIb | Medical Device | 2024-07-01 | 2025-06-30 | 1 year | 2026-03-06 | In progress | Terence | None | none | -31 | 🔴 OVERDUE | Q1 2026 | 50 | ⚠️ YES
TBD | TD087 | PSUR087 | LifeGlobal Dishes GPS® Dishware | IIa | Media | 2024-06-01 | 2026-05-31 | 2 years | 2026-06-26 | Not Started | Jeff | None | none | 81 | 🟢 ON TRACK | Q2 2026 | 0 | No
TBD | TD069 | PSUR069 | Lone Star Elastic Stays | IIa | Fertility | 2024-04-01 | 2026-03-31 | 2 years | 2026-06-06 | Not Started | Venkata | None | none | 61 | 🟢 ON TRACK | Q2 2026 | 0 | No
TBD | TD082 | PSUR082 | Pessary Product Family | IIb | Medical Device | 2022-04-01 | 2025-11-30 | 1 year | 2026-02-23 | Completed | Venkata | None | none | - | ✅ DONE | Q1 2026 | 100 | No
TBD |  | PSUR068 | Wallace Aspiration Pump | I | TBD |  |  | TBD | 04/30/2026 - Immediate | Not Started | Jeff | None | No available documents released in MC | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD073 | PSUR073 | IVF PASTEUR PIPETTES | IIa | Medical Device | 2024-07-01 | 2026-06-30 | 2 years | 2026-08-07 | Not Started | TBD | None | none | 123 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD083 | PSUR083 | LifeDop Dopplers and Probes | IIa | Medical Device | 2023-08-01 | 2025-07-31 | 2 years | 2026-03-27 | In progress | Jeff | None | none | -10 | 🔴 OVERDUE | Q1 2026 | 50 | ⚠️ YES
TBD | TD007 | PMS007R | Adult-Neonatal_Care | I | Medical Device |  |  | TBD | 2026-01-03 | Not Started | Jeff | None | none | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD059 | PSUR059 | Assisted Reproduction Catheters | I | Medical Device |  |  | 3 years | 4/30/2026 - Immediate | Not Started | Jeff | None | No available documents released in MC | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD103 | PSUR103 | Micropipettes, Biopsy, ICISI Assisted Hatching (Mechanical and Chemical) Holding | IIb | Medical Device | 2022-04-01 | 2025-12-31 | 1 year | 2/20/2026 - Immediate | Completed | Terence | None | CER deadline 19 January 2026 | - | ✅ DONE | TBD | 100 | No
TBD | TD129 | PSUR129 | Cook Doppler blood flow monitor products | IIb | Medical Device | 2024-09-01 | 2025-08-31 | 1 year | 2026-02-27 | In Review | Terence | None |  | -38 | 🔴 OVERDUE | Q1 2026 | 0 | ⚠️ YES
TBD | TD104 | PSUR104 | HBA Biocoat | I | TBD |  |  | TBD | 2026-03-20 | In progress | Terence | None | No available documents released in MC | -17 | 🔴 OVERDUE | Q1 2026 | 50 | ⚠️ YES
TBD | TD105 | PSUR105 | Stripper Tips | IIB | Medical Device | 2025-07-01 | 2026-06-30 | 1 year | 2026-07-31 | Not Started | TBD | None |  | 116 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD118 | PSUR118 | OBP AnoSpec Lighted Anoscopes | I | Medical Device |  |  | 3 years | 03/27/2026 - Immediate | Not Started | Terence | None | No documents available in MC | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD121 | PSUR121 | Disposable Vaginal Speculums | I | Medical Device |  |  | 3 years | 3/24/2026 - Immediate | Not Started | Venkata | None | none | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD016 | PSUR016 | PICSI® Sperm Selection Device | III | Fertility | 2025-04-01 | 2026-03-31 | 1 year | 2026-06-30 | Not Started | Harish | None | none | 85 | 🟢 ON TRACK | Q2 2026 | 0 | No
TBD | TD130 | PSUR130 | TD130 Bakri Postpartum Balloon | IIa | Medical Device | 2024-07-01 | 2026-06-30 | 2 years | 2026-07-25 | Not Started | TBD | None |  | 110 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD131 | PSUR131 | TD131_Cervical Ripening Balloon (CRB) Products | IIa | Medical Device | 2024-09-01 | 2026-08-31 | 2 years | 2026-11-06 | Not Started | TBD | None |  | 214 | 🟢 ON TRACK | Q4 2026 | 0 | No
TBD | TD144 | PSUR144 | ONETRAC & ONETRAC LX | IIa | TBD |  |  | 2 years | 2/27/2026 - Immediate | In progress | Terence | None | Per Jennifer tracking file need to reach out to Nancy Lynch | N/A | ⚪ TBD | TBD | 50 | No
TBD | TD144 | PSUR145 | Unknown | I | TBD |  |  | TBD | 2/27/2026 - Immediate | In progress | Terence | None | Per Jennifer tracking file need to reach out to Nancy Lynch | N/A | ⚪ TBD | TBD | 50 | No
TBD | TD147 | PSUR147 | Global Total and Global HP | III | Media(NON CE-MARKED) | 2025-07-01 | 2026-06-30 | 1 year | 2026-07-30 | Not Started | TBD | None |  | 115 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD148 | PSUR148 | Global Total Fert | III | Media(NON CE-MARKED) | 2025-07-01 | 2026-06-30 | 1 year | 2026-08-21 | Not Started | TBD | None |  | 137 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD149 | PSUR149 | Global Total™ with HEPES, 50mL, 100mL HTF w/ HEPES, 100 mL, 500 mL Washing mHTF with HEPES & Phenol Red, 100mL, 500mL | III | Media(NON CE-MARKED) | 2025-07-01 | 2026-06-30 | 1 year | 2026-08-28 | Not Started | TBD | None |  | 144 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD150 | PSUR150 | LifeGlobal™ Protein Supplement, 20mL LifeGlobal™ Protein Supplement, 50mL LifeGlobal™ Protein Supplement, 6 x 5mL Quinn's Advantage™ SPS Serum Protein Substitute 100 ml Quinn's Advantage™ SPS Serum Protein Substitute Kit, 12 x 12mL | III | Media(NON CE-MARKED) | 2025-07-01 | 2026-06-30 | 1 year | 2026-09-18 | Not Started | TBD | None |  | 165 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD151 | PSUR151 | Hyaluronidase, 6 x 1 ml | III | Media(NON CE-MARKED) | 2025-07-01 | 2026-06-30 | 1 year | 2026-09-25 | Not Started | TBD | None |  | 172 | 🟢 ON TRACK | Q3 2026 | 0 | No
TBD | TD005 | PMS005R | RI Syringes | I | Fertility | 2021-06-01 | 2026-05-31 | 3 years | 2026-06-06 | Assigned | Harish | None | none | N/A | ⚪ TBD | TBD | 25 | No
MDR 768070 | TD041 | PSUR205 | Oil for tissue Culture | IIa | Media | 2024-07-01 | 2026-06-30 | 2 years | 2026-05-15 | Not Started | Terence | Combine in PSUR041 | PSUR041, PSUR205, PSUR301, PSUR302 and PSUR303 are combined in PSUR041 | 39 | 🟡 SOON | Q2 2026 | 0 | No
TBD | TD122 | PSUR122 | Lighted Endoscopic Products | I | Medical Device |  |  | 3 years | 3/27/2026 - Immediate | Not Started | Harish | None | none | N/A | ⚪ TBD | TBD | 0 | No
TBD | TD062 | PSUR062 | Endometrial Suction Curette Product Family | I | Medical Device | 2023-09-30 | 2028-09-29 | 3 years | 4/11/2026 - Immediate | Assigned | Harish | None | No available documents released in MC | N/A | ⚪ TBD | TBD | 25 | No
MDR 768184 | TD045 | PSUR045 | ORIGIO® Handling™ | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-08-07 | Not Started | TBD | Combined PSUR | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | 123 | 🟢 ON TRACK | Q3 2026 | 0 | No
MDR 768070 | TD041 | PSUR301 | LifeGuard® Oil | IIa | Media | 2023-07-01 | 2025-06-30 | 2 years | 2026-05-15 | Not Started | Terence | Combine in PSUR041 | PSUR041, PSUR205, PSUR301, PSUR302 and PSUR303 are combined in PSUR041 | 39 | 🟡 SOON | Q2 2026 | 0 | No
MDR 768070 | TD041 | PSUR302 | LiteOil® | IIa | Media | 2024-01-01 | 2025-12-31 | 2 years | 2026-05-15 | Not Started | Terence | Combine in PSUR041 | PSUR041, PSUR205, PSUR301, PSUR302 and PSUR303 are combined in PSUR041 | 39 | 🟡 SOON | Q2 2026 | 0 | No
MDR 768070 | TD041 | PSUR303 | Paraffin Oil P.G. | IIa | Media | 2024-01-01 | 2025-12-31 | 2 years | 2026-05-15 | Not Started | Terence | Combine in PSUR041 | PSUR041, PSUR205, PSUR301, PSUR302 and PSUR303 are combined in PSUR041 | 39 | 🟡 SOON | Q2 2026 | 0 | No
MDR 768184 | TD045 | PSUR214 | Quinn's Advantage Medium with HEPES | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-08-07 | Not Started | TBD | Combined PSUR | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | 123 | 🟢 ON TRACK | Q3 2026 | 0 | No
MDR 768184 | TD045 | PSUR310 | LG global total LP w/ HEPES | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-08-07 | Not Started | TBD | Combined PSUR | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | 123 | 🟢 ON TRACK | Q3 2026 | 0 | No
MDR 768184 | TD045 | PSUR311 | LG global w/ HEPES | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-08-07 | Not Started | TBD | Combined PSUR | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | 123 | 🟢 ON TRACK | Q3 2026 | 0 | No
MDR 768186 | TD117 | PSUR215 | Quinn's Advantage™ Thaw Kit | III | Media | 2024-01-01 | 2025-12-31 | 1 year | 2026-03-31 | In Review | Harish | Combined PSUR | BSI submissiom 18 May 2026, Writed to check to combine 2024 and 2025 | -6 | 🟠 URGENT | Q1 2026 | 0 | ⚠️ YES
MDR 768190 | TD053 | PSUR053 | INSORB Skin Stapler and Forceps | III | TBD | 2025-05-01 | 2026-04-30 | 1 year | 2026-05-13 | Not Started | Venkata | None | BSI submission on 17 May 2026 | 37 | 🟡 SOON | Q2 2026 | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
[14 empty] | N/A | ⚪ TBD | TBD | 0 | No
Formulas:
Days Remaining = IF([Status]="Completed","-",IF(ISNUMBER([Due Date]),[Due Date]-TODAY(),"N/A"))

## BSI Dashboard
📊 BSI PSUR DASHBOARD — Q1 & Q2 2026
KEY PERFORMANCE INDICATORS
Total BSI Certificates |  | Completed |  | In Progress |  | In Review |  | Not Started |  | Overdue |  | Overall Progress
23 |  | 7 |  | 1 |  | 3 |  | 11 |  | 0 |  | 30.43%
📊 STATUS BREAKDOWN |  |  |  | 👤 WRITER WORKLOAD |  |  |  | 📅 QUARTERLY VIEW
Status | Count | % of Total |  | Writer | Assigned | Completed |  | Quarter | Total | Completed | % Done
Completed | 7 | 30.43% |  | Harish | 9 | 5 |  | Q1 2026 | 9 | 8 | 88.89%
In progress | 1 | 4.348% |  | Jeff | 3 | 2 |  | Q2 2026 | 11 | 0 | 0%
In Review | 3 | 13.04% |  | Venkata | 7 | 1 |  | Other | 4 | 0 | 0%
Assigned | 0 | 0% |  | Terence | 2 | 0 |  | TOTAL | 24 | 8 | 33.33%
Not Started | 11 | 47.83% |  | TOTAL | 21 | 8
TBD | 1 | 4.348%
🎯 DEVICE CLASS BREAKDOWN |  |  |  | ⚡ PRIORITY BREAKDOWN |  |  |  | ⏰ NEXT 30 DAYS - CRITICAL DEADLINES
Class | Count | % of Total |  | Priority | Count | % of Total |  | Metric | Count
Class III | 23 | 100% |  | 🔴 OVERDUE | 0 | 0% |  | Due in 7 days | 2
Class IIb | 0 | 0% |  | 🟠 URGENT | 6 | 26.09% |  | Due in 14 days | 3
Class IIa | 1 | 4.348% |  | 🟡 SOON | 3 | 13.04% |  | Due in 30 days | 6
Class I / Is | 0 | 0% |  | 🟢 ON TRACK | 7 | 30.43% |  | Currently Overdue | 0
|  |  |  | ✅ DONE | 7 | 30.43% |  | Avg Days to Deadline | 62.625
|  |  |  | ⚪ TBD | 0 | 0%
📈 STATUS DISTRIBUTION |  |  |  | 📊 WRITER WORKLOAD |  |  |  | ⚡ PRIORITY DISTRIBUTION
⏱️ Dashboard auto-updates when you change Status, Due Date, or Writer on the 'BSI PSURs' sheet
Status | Count |  | Writer | Assigned | Completed |  | Priority | Count
Completed | 7 |  | Harish | 9 | 5 |  | OVERDUE | 0
In Progress | 1 |  | Jeff | 3 | 2 |  | URGENT | 6
In Review | 3 |  | Venkata | 7 | 1 |  | SOON | 3
Not Started | 11 |  | Terence | 2 | 0 |  | ON TRACK | 7
TBD | 1 | [5 empty] | DONE | 7
[7 empty] | TBD | 0

## Writer Workload (hidden)
👤 WRITER WORKLOAD TRACKER
Writer | Total Assigned | Completed | In Progress | Not Started | TBD | Overdue | Completion Rate | Avg Days Left | Earliest Due | Risk Level
Harish | 3 | 0 | 1 | 1 | 0 | 1 | 0% | 40 | 2026-03-31 | 🟠 MEDIUM
Jeff | 10 | 0 | 2 | 7 | 0 | 3 | 0% | 21 | 2026-02-27 | 🔴 HIGH
Venkata | 7 | 1 | 2 | 4 | 0 | 3 | 14.29% | 0 | 2026-02-20 | 🔴 HIGH
Terence | 12 | 2 | 5 | 1 | 0 | 4 | 16.67% | -23 | 2026-02-27 | 🔴 HIGH
TOTAL | 32 | 3 | 10 | 13 | 0 | 11 | 9.375%
📝 DETAILED ASSIGNMENTS BY WRITER (Live-linked to Master Schedule)
Writer | PSUR ID | Product Name | Class | Due Date | Days Left | Status | Priority | Overdue? | Combined PSUR | Notes
Harish | PSUR039 | Acidified Tyrodes Solution (1060) | III | 2026-03-31 | -6 | In progress | 🟠 URGENT | ⚠️ YES | None | none
Harish | PSUR016 | PICSI® Sperm Selection Device | III | 2026-06-30 | 85 | Not Started | 🟢 ON TRACK | No | None | none
Harish | PMS005R | RI Syringes | I | 2026-06-06 | N/A | Assigned | ⚪ TBD | No | None | none
Jeff | PSUR041 | Liquid Paraffin - CHANGE CURRENT REV C TO B AND B TO A | IIa | 2026-05-15 | 39 | Not Started | 🟡 SOON | No | Combine in PSUR041 | PSUR041, PSUR205, PSUR301, PSUR302 and PSUR303 are combined in PSUR041
Jeff | PSUR044 | VitriFit™ | IIa | 2026-05-08 | 32 | Not Started | 🟡 SOON | No | None | none
Jeff | PSUR050 | RI Witness EHP | IIa | 2026-02-27 | -38 | In Review | 🔴 OVERDUE | ⚠️ YES | None | In draft, need to release 3-6-26 Awaiting Sales/complaint data, updating to new template
Jeff | PSUR071 | Mobius Elastic Retractors | IIa | 2026-03-13 | -24 | In progress | 🔴 OVERDUE | ⚠️ YES | None | Sales data request issued 3-24-26
Jeff | PSUR058 | Apple-Hunt Trocars | IIa | 2026-06-13 | 68 | Not Started | 🟢 ON TRACK | No | None | none
Jeff | PSUR087 | LifeGlobal Dishes GPS® Dishware | IIa | 2026-06-26 | 81 | Not Started | 🟢 ON TRACK | No | None | none
Jeff | PSUR068 | Wallace Aspiration Pump | I | 04/30/2026 - Immediate | N/A | Not Started | ⚪ TBD | No | None | No available documents released in MC
Jeff | PSUR083 | LifeDop Dopplers and Probes | IIa | 2026-03-27 | -10 | In progress | 🔴 OVERDUE | ⚠️ YES | None | none
Jeff | PMS007R | Adult-Neonatal_Care | I | 2026-01-03 | N/A | Not Started | ⚪ TBD | No | None | none
Jeff | PSUR059 | Assisted Reproduction Catheters | I | 4/30/2026 - Immediate | N/A | Not Started | ⚪ TBD | No | None | No available documents released in MC
TBD | PSUR007 | LoneStar Retractor Kit | IIa | 2026-02-20 | -45 | In progress | 🔴 OVERDUE | ⚠️ YES | None | 0
TBD | PMS007R | Retractors | Is | 0 | N/A | Not Started | ⚪ TBD | No | Combine with PSUR007 | 0
TBD | PMS062R | Endometrial_Suction_Curette | I | Immediate | N/A | Not Started | ⚪ TBD | No | None | No available documents released in MC
TBD | PMS123R | K-Systems Flex Short-term Incubator Module | I | 0 | N/A | Not Started | ⚪ TBD | No | None | Terence will be conforming
TBD | PMS124R | Embryo Biopsy Kit | I | 0 | N/A | Not Started | ⚪ TBD | No | None | Terence will be conforming
TBD | PMS125R | Endometrial Biopsy Kit | I | 0 | N/A | Not Started | ⚪ TBD | No | None | Terence will be conforming
TBD | PSUR018 | LEEP ELECTRODES | IIb | 2026-09-25 | 172 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR047 | SynVitro® Hyadase | III | 2026-07-30 | 115 | Not Started | 🟢 ON TRACK | No | None | none
TBD | PSUR048 | Integra 3 Micromanipulator | IIa | 2026-07-30 | 115 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR060 | Carter-Thomason Port Closure Products | IIa | 2026-08-28 | 144 | Not Started | 🟢 ON TRACK | No | None | none
TBD | PSUR073 | IVF PASTEUR PIPETTES | IIa | 2026-08-07 | 123 | Not Started | 🟢 ON TRACK | No | None | none
TBD | PSUR105 | Stripper Tips | IIB | 2026-07-31 | 116 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR130 | TD130 Bakri Postpartum Balloon | IIa | 2026-07-25 | 110 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR131 | TD131_Cervical Ripening Balloon (CRB) Products | IIa | 2026-11-06 | 214 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR147 | Global Total and Global HP | III | 2026-07-30 | 115 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR148 | Global Total Fert | III | 2026-08-21 | 137 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR149 | Global Total™ with HEPES, 50mL, 100mL HTF w/ HEPES, 100 mL, 500 mL Washing mHTF with HEPES & Phenol Red, 100mL, 500mL | III | 2026-08-28 | 144 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR150 | LifeGlobal™ Protein Supplement, 20mL LifeGlobal™ Protein Supplement, 50mL LifeGlobal™ Protein Supplement, 6 x 5mL Quinn's Advantage™ SPS Serum Protein Substitute 100 ml Quinn's Advantage™ SPS Serum Protein Substitute Kit, 12 x 12mL | III | 2026-09-18 | 165 | Not Started | 🟢 ON TRACK | No | None | 0
TBD | PSUR151 | Hyaluronidase, 6 x 1 ml | III | 2026-09-25 | 172 | Not Started | 🟢 ON TRACK | No | None | 0
Terence | PMS002R | Leisegang Coloscopes | I | 2026-04-01 | -5 | In progress | 🟠 URGENT | ⚠️ YES | None | none
Terence | PMS003R | Ally Uterine Positioning System | I | 2026-01-15 | N/A | In Review | ⚪ TBD | No | None | Determining the denominator
Terence | PMS008R | Endosee Hysteroscopy Product Family | I | 2026-03-01 | - | Completed | ✅ DONE | No | None | 0
Terence | PMS009R | Comfit Trake - Nofit, NEO-prep | I | 0 | N/A | In Review | ⚪ TBD | No | 0 | 0
Terence | PMSR017 | EZ-Grip & Comfort Rest | I | 2026-01-23 | N/A | In Review | ⚪ TBD | No | None | Need to check with Terence
Terence | PSUR081 | Fischer cone Biopsy Electrodes | IIb | 2026-03-06 | -31 | In progress | 🔴 OVERDUE | ⚠️ YES | None | none
Terence | PSUR103 | Micropipettes, Biopsy, ICISI Assisted Hatching (Mechanical and Chemical) Holding | IIb | 2/20/2026 - Immediate | - | Completed | ✅ DONE | No | None | CER deadline 19 January 2026
Terence | PSUR129 | Cook Doppler blood flow monitor products | IIb | 2026-02-27 | -38 | In Review | 🔴 OVERDUE | ⚠️ YES | None | 0
Terence | PSUR104 | HBA Biocoat | I | 2026-03-20 | -17 | In progress | 🔴 OVERDUE | ⚠️ YES | None | No available documents released in MC
Terence | PSUR118 | OBP AnoSpec Lighted Anoscopes | I | 03/27/2026 - Immediate | N/A | Not Started | ⚪ TBD | No | None | No documents available in MC
Terence | PSUR144 | ONETRAC & ONETRAC LX | IIa | 2/27/2026 - Immediate | N/A | In progress | ⚪ TBD | No | None | Per Jennifer tracking file need to reach out to Nancy Lynch
Terence | PSUR145 | Unknown | I | 2/27/2026 - Immediate | N/A | In progress | ⚪ TBD | No | None | Per Jennifer tracking file need to reach out to Nancy Lynch
Venkata | PSUR049 | Saturn 5 Laser System | IIb | 2026-03-13 | -24 | Not Started | 🔴 OVERDUE | ⚠️ YES | None | CER deadline 02 March 2026
Venkata | PSUR070 | Medical Heatpacks | IIa | 2026-02-27 | -38 | In progress | 🔴 OVERDUE | ⚠️ YES | None | none
Venkata | PSUR051 | EZ-Range Pipettes | IIb | 2026-05-22 | 46 | Not Started | 🟡 SOON | No | None | none
Venkata | PSUR077 | Wallace Oocyte Recovery/Collection Sets | IIa | 2026-02-20 | -45 | In progress | 🔴 OVERDUE | ⚠️ YES | None | Routing in MC
Venkata | PSUR069 | Lone Star Elastic Stays | IIa | 2026-06-06 | 61 | Not Started | 🟢 ON TRACK | No | None | none
Venkata | PSUR082 | Pessary Product Family | IIb | 2026-02-23 | - | Completed | ✅ DONE | No | None | none
Venkata | PSUR121 | Disposable Vaginal Speculums | I | 3/24/2026 - Immediate | N/A | Not Started | ⚪ TBD | No | None | none

## Timeline (hidden)
📅 PSUR TIMELINE — Q1 & Q2 2026 GANTT VIEW
PSUR ID | Writer | Status | Due Date | Jan 1H | Jan 2H | Feb 1H | Feb 2H | Mar 1H | Mar 2H | Apr 1H | Apr 2H | May 1H | May 2H | Jun 1H | Jun 2H | Jul+ | Days Left
PMS002R | Terence | In progress | 2026-04-01 | [6 empty] | █ | [6 empty] | -5
PMS003R | Terence | In Review | 2026-01-15 | [13 empty] | N/A
PSUR007 | TBD | In progress | 2026-02-20 |  |  |  | █ | [9 empty] | -45
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PMS007R | TBD | Not Started | 0 | [13 empty] | N/A
PMS008R | Terence | Completed | 2026-03-01 | [13 empty] | -
PMS009R | Terence | In Review | 0 | [13 empty] | N/A
PMS062R | TBD | Not Started | Immediate | [13 empty] | N/A
PMS123R | TBD | Not Started | 0 | [13 empty] | N/A
PMS124R | TBD | Not Started | 0 | [13 empty] | N/A
PMS125R | TBD | Not Started | 0 | [13 empty] | N/A
PMSR017 | Terence | In Review | 2026-01-23 | [13 empty] | N/A
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR018 | TBD | Not Started | 2026-09-25 | [12 empty] | █ | 172
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR039 | Harish | In progress | 2026-03-31 | [5 empty] | █ | [7 empty] | -6
PSUR041 | Jeff | Not Started | 2026-05-15 | [8 empty] | █ |  |  |  |  | 39
PSUR044 | Jeff | Not Started | 2026-05-08 | [8 empty] | █ |  |  |  |  | 32
PSUR049 | Venkata | Not Started | 2026-03-13 |  |  |  |  | █ | [8 empty] | -24
PSUR050 | Jeff | In Review | 2026-02-27 |  |  |  | █ | [9 empty] | -38
PSUR070 | Venkata | In progress | 2026-02-27 |  |  |  | █ | [9 empty] | -38
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR047 | TBD | Not Started | 2026-07-30 | [12 empty] | █ | 115
PSUR048 | TBD | Not Started | 2026-07-30 | [12 empty] | █ | 115
PSUR071 | Jeff | In progress | 2026-03-13 |  |  |  |  | █ | [8 empty] | -24
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR051 | Venkata | Not Started | 2026-05-22 | [9 empty] | █ |  |  |  | 46
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR077 | Venkata | In progress | 2026-02-20 |  |  |  | █ | [9 empty] | -45
PSUR058 | Jeff | Not Started | 2026-06-13 | [10 empty] | █ |  |  | 68
PSUR060 | TBD | Not Started | 2026-08-28 | [12 empty] | █ | 144
PSUR081 | Terence | In progress | 2026-03-06 |  |  |  |  | █ | [8 empty] | -31
PSUR087 | Jeff | Not Started | 2026-06-26 | [11 empty] | █ |  | 81
PSUR069 | Venkata | Not Started | 2026-06-06 | [10 empty] | █ |  |  | 61
PSUR082 | Venkata | Completed | 2026-02-23 |  |  |  | █ | [9 empty] | -
PSUR068 | Jeff | Not Started | 04/30/2026 - Immediate | [13 empty] | N/A
PSUR073 | TBD | Not Started | 2026-08-07 | [12 empty] | █ | 123
PSUR083 | Jeff | In progress | 2026-03-27 | [5 empty] | █ | [7 empty] | -10
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PMS007R | Jeff | Not Started | 2026-01-03 | [13 empty] | N/A
PSUR059 | Jeff | Not Started | 4/30/2026 - Immediate | [13 empty] | N/A
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR103 | Terence | Completed | 2/20/2026 - Immediate | [13 empty] | -
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR129 | Terence | In Review | 2026-02-27 |  |  |  | █ | [9 empty] | -38
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR104 | Terence | In progress | 2026-03-20 | [5 empty] | █ | [7 empty] | -17
PSUR105 | TBD | Not Started | 2026-07-31 | [12 empty] | █ | 116
PSUR118 | Terence | Not Started | 03/27/2026 - Immediate | [13 empty] | N/A
PSUR121 | Venkata | Not Started | 3/24/2026 - Immediate | [13 empty] | N/A
PSUR016 | Harish | Not Started | 2026-06-30 | [11 empty] | █ |  | 85
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PSUR130 | TBD | Not Started | 2026-07-25 | [12 empty] | █ | 110
PSUR131 | TBD | Not Started | 2026-11-06 | [12 empty] | █ | 214
LEGEND: | █ Completed | █ In Progress | █ Not Started | █ TBD |  | Today: | 2026-04-06 | Total PSURs: | 77

## BSI PSURs
MDR Certificate | TD | PSUR/PMSR ID | Product Name | Class | Type | Start Period | End Period | Frequency | Due Date | Status | Writer | Combined PSUR | Notes | Days Remaining | Priority | Quarter | Completion % | Overdue?
MDR 768142 | TD019 | PSUR019 | Blast Freeze/BlastThaw | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-05-22 | In progress | Harish | None | BSI submissiom 18 May 2026 | 46 | 🟡 SOON | Q2 2026 | 50 | No
MDR 768143 | TD022 | PSUR022 | Embryo Freezing & Thawing Pack | III | Media | 2024-07-01 | 2025-12-31 | 1 year | 2026-05-18 | Not Started | Venkata | None | BSI submissiom 18 May 2026, this reporting is completed in old template need to complete in new template Stefania is asking for the latest data till December 2025 | 42 | 🟡 SOON | Q2 2026 | 0 | No
MDR 768144 | TD031 | PSUR031 | SpermSlow™ (1094) | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-04-08 | In Review | Terence | None | BSI submission on 08 April 2026 | 2 | 🟠 URGENT | Q2 2026 | 0 | No
MDR 768145 | TD026 | PSUR026 | MediCult IVM® System (8221) | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-02-06 | Completed | Harish | None | BSI submissiom 11 February 2026 | - | ✅ DONE | Q1 2026 | 100 | No
MDR 768146 | TD011 | PSUR011 | Biopsy Medium | III | Media | 2025-07-01 | 2026-06-30 | Annually | 2026-07-24 | Not Started | Terence | None | BSI submission 23 October 2026 | 109 | 🟢 ON TRACK | Q3 2026 | 0 | No
MDR 768148 | TD033 | PSUR033 | Universal IVF Medium (1030 & 1031) | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-05-08 | Not Started | Harish | None | BSI submissiom 12 November 2026 | 32 | 🟡 SOON | Q2 2026 | 0 | No
MDR 768150 | TD034 | PSUR034 | UTM™ Transfer Medium (1052/1152) | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-10-09 | Not Started | Venkata | None | BSI submission 23 October 2026 | 186 | 🟢 ON TRACK | Q4 2026 | 0 | No
MDR 768152 | TD025 | PSUR025 | ICSI Cumulase | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-04-08 | In Review | Harish | None | BSI submissiom 08 April 2026 | 2 | 🟠 URGENT | Q2 2026 | 0 | No
MDR 768153 | TD028 | PSUR027 | PVP Clinical Grade (1090) | III | Media | 2024-01-01 | 2025-12-31 | 1 year | 2026-02-06 | Completed | Harish | None | BSI submissiom 11 February 2026 Combine PSUR027, PSUR028, PSUR200 This report for last year is not yet released,Lets combine PSUR027, PSUR028, PSUR200 for 2025, we need to release 2024. | - | ✅ DONE | Q1 2026 | 100 | No
| TD028 | PSUR028 | PVP Medium (1089) | [8 empty] | None | BSI submissiom 11 February 2026 Combine PSUR027, PSUR028, PSUR200 This report for last year is not yet released,Lets combine PSUR027, PSUR028, PSUR200 for 2025, we need to release 2024. | N/A | ✅ DONE | TBD | 0 | No
| TD028 | PSUR200 | PVP™ 7% Ready to Use Solution Kit (ART-4005-A) | [8 empty] | Combined PSUR | BSI submissiom 11 February 2026 Combine PSUR027, PSUR028, PSUR200 This report for last year is not yet released,Lets combine PSUR027, PSUR028, PSUR200 for 2025, we need to release 2024. | N/A | ✅ DONE | TBD | 0 | No
MDR 768161 | TD021 | PSUR021 | Cryosperm (1101) | III | Media | 2024-01-01 | 2025-12-31 | 1 year | 2026-02-06 | Completed | Jeff | Combined PSUR | BSI submissiom 11 February 2026 Combine PSUR021, PSUR201, PSUR029, We can have next surveillanc eperiod 1/1/2025 to 12/31/2025 | - | ✅ DONE | Q1 2026 | 100 | No
| TD021 | PSUR029 | Sperm Freezing Medium | [9 empty] | BSI submissiom 11 February 2026 Combine PSUR021, PSUR201, PSUR029, We can have next surveillanc eperiod 1/1/2025 to 12/31/2025 | N/A | ✅ DONE | TBD | 0 | No
| TD021 | PSUR201 | Quinn's Advantage™ Sperm Freezing Medium | [9 empty] | BSI submissiom 11 February 2026 Combine PSUR021, PSUR201, PSUR029, We can have next surveillanc eperiod 1/1/2025 to 12/31/2025 | N/A | ✅ DONE | TBD | 0 | No
MDR 768165 | TD020 | PSUR020 | Flushing Medium with Heparin | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-04-24 | Not Started | Jeff | Combined PSUR | BSI submissiom 19 December 2026, PSUR020, PSUR023, PSUR032 and PSUR300 are combined in PSUR020 | 18 | 🟠 URGENT | Q2 2026 | 0 | No
| TD020 | PSUR023 | SynVitro Flush with Heparin | [6 empty] | Not Started |  | Combined PSUR | BSI submissiom 19 December 2026, PSUR020, PSUR023, PSUR032 and PSUR300 are combined in PSUR020 | N/A | 🟠 URGENT | TBD | 0 | No
| TD020 | PSUR032 | SynVitro Flush (1584) | [6 empty] | Not Started |  | None | BSI submissiom 19 December 2026, PSUR020, PSUR023, PSUR032 and PSUR300 are combined in PSUR020 | N/A | 🟠 URGENT | TBD | 0 | No
| TD020 | PSUR300 | LG global collect | [6 empty] | TBD |  | PSUR020 | BSI submissiom 19 December 2026, PSUR020, PSUR023, PSUR032 and PSUR300 are combined in PSUR020 | N/A | 🟠 URGENT | TBD | 0 | No
MDR 768166 | TD094 | PSUR030 | Origio Sperm Preparation Medium (1069/1070) | III | Media | 2024-01-01 | 2025-01-31 | 1 year | 2026-01-09 | Completed | Venkata | Combined PSUR | BSI submissiom 09 January 2026 Combine PSUR030, PSUR094, PSUR202 CER deadline 17 March 2026, Combine PSUR030, PSUR094, PSUR202 Need to align on the data collection period 2 PSURs are Jan to Dec 2024, 1 PSUR is Feb 2024 to Jan 2025 | - | ✅ DONE | Q1 2026 | 100 | No
| TD094 | PSUR094 | Origio Sperm Wash (8405) | [9 empty] | BSI submissiom 09 January 2026 Combine PSUR030, PSUR094, PSUR202 CER deadline 17 March 2026, Combine PSUR030, PSUR094, PSUR202 Need to align on the data collection period 2 PSURs are Jan to Dec 2024, 1 PSUR is Feb 2024 to Jan 2025 | N/A | ✅ DONE | TBD | 0 | No
| TD094 | PSUR202 | Quinn's Sperm Washing Medium | [9 empty] | BSI submissiom 09 January 2026 Combine PSUR030, PSUR094, PSUR202 CER deadline 17 March 2026, Combine PSUR030, PSUR094, PSUR202 Need to align on the data collection period 2 PSURs are Jan to Dec 2024, 1 PSUR is Feb 2024 to Jan 2025 | N/A | ✅ DONE | TBD | 0 | No
TBD | TD076 | PSUR076 | Vacuum Assisted Delivery System | IIa | Medical Device | 2024-06-01 | 2025-12-31 | 2 years | 2026-02-20 | Completed | Harish | None | Updated the PSUR early for BSI surveillance audit | - | ✅ DONE | Q1 2026 | 100 | No
MDR 768167 | TD035 | PSUR035 | ORIGIO® Sequential Blast™ | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-07-30 | Not Started | TBD | PSUR035 | BSI submission 23 October 2026, PSUR035 and PSUR204 are combined in PSUR035 | 115 | 🟢 ON TRACK | Q3 2026 | 0 | No
| TD035 | PSUR204 | Quinn’s Advantage™ Blastocyst Medium (ART-1029) | [9 empty] | BSI submissiom 23 October 2026, PSUR035 and PSUR204 are combined in PSUR035 | N/A | 🟢 ON TRACK | TBD | 0 | No
MDR 768172 | TD037 | PSUR037 | ORIGIO® Sequential Fert™ | III | Media | 2024-01-01 | 2024-12-31 | 1 year | 2026-01-09 | Completed | Harish | Combined PSUR | BSI submissiom 09 January 2026 Combine PSUR037, PSUR206, PSUR304 | - | ✅ DONE | Q1 2026 | 100 | No
MDR 768173 | TD036 | PSUR036 | ORIGIO® Sequential Cleav™ | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-06-20 | Not Started | Venkata | None | BSI submissiom 12 November 2026, PSUR036 and PSUR0208 are combined in PSUR036 | 75 | 🟢 ON TRACK | Q2 2026 | 0 | No
| TD036 | PSUR208 | Quinn’s Advantage™ Cleavage Medium | [7 empty] | Harish | PSUR036 | BSI submissiom 12 November 2026, PSUR036 and PSUR0208 are combined in PSUR036 | N/A | 🟢 ON TRACK | TBD | 0 | No
MDR 768174 | TD095 | PSUR095 | ORIGIO® Gradient™ 100, ORIGIO® Gradient™ 90 , and ORIGIO® Gradient™ 40/80 / Density gradient product family | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-04-17 | TBD | Venkata | PSUR095 | CER deadline 13 April 2026. BSI submissiom 12 November 2026, PSUR095 and PSUR0209 are combined in PSUR095 | 11 | 🟠 URGENT | Q2 2026 | 0 | No
| TD095 | PSUR209 | PureCeption 24-determination Kit, 40% Upper Phase, 80% Lower Phase, 100% Isotonic Solution | [9 empty] | CER deadline 13 April 2026. BSI submissiom 12 November 2026, PSUR095 and PSUR0209 are combined in PSUR095 | N/A | 🟠 URGENT | TBD | 0 | No
MDR 768176 | TD102 | PSUR102 | EmbryoGen, BlastGen, EmbryoGen® & BlastGen | III | Media | 2024-05-01 | 2025-04-30 | 1 year | 2026-01-09 | Completed | Harish | None | BSI submissiom 05 January 2026, CER deadline 13 March 2026 | - | ✅ DONE | Q1 2026 | 100 | No
MDR 768180 | TD114 | PSUR212 | Human Serum Albumin (ART-3001) (ART-3003) HSA 12 x 5 ml (GHSA-125) | III | Media | 2024-07-01 | 2025-06-30 | 1 year | 2026-03-31 | Completed | Jeff | PSUR212 | BSI submissiom 08 April 2026, PSUR212 and PSUR306 are addressed in PSUR212 3-6-26 Currently in Stakeholder Review | - | ✅ DONE | Q1 2026 | 100 | No
| TD114 | PSUR306 | HSA 12 x 5 ml (GHSA-125) | [9 empty] | BSI submissiom 08 April 2026, PSUR212 and PSUR306 are addressed in PSUR212 | N/A | ✅ DONE | TBD | 0 | No
MDR 768181 | TD092 | PSUR092 | Medicult Vitrification Cooling, MediCult Vitrification Warming Sage™ Vitrification Kit (ART-8026), Sage™ Vitrification Warming Kit, Sage ViaBl SuperFast Blastocyst Warming Media (ART-8035) | III | Media | 2025-01-01 | 2025-12-31 | 1 year | 2026-06-26 | Not Started | Venkata | Combined PSUR | BSI submissiom 19 December 2026, PSUR213 and PSUR092 are combined in PSUR092 | 81 | 🟢 ON TRACK | Q2 2026 | 0 | No
| TD092 | PSUR213 | Sage™ Vitrification Kit (ART-8026), Sage™ Vitrification Warming Kit, Sage ViaBl SuperFast Blastocyst Warming Media (ART-8035) | [9 empty] | BSI submissiom 19 December 2026, PSUR213 and PSUR092 are combined in PSUR092 | N/A | 🟢 ON TRACK | TBD | 0 | No
MDR 768183 | TD089 | PSUR046 | Sage 1-Step GM-CSF | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-07-22 | Not Started | TBD | Combined PSUR | BSI submissiom 28 July 2026, PSUR046, PSUR089, PSUR308 and PSUR309 are combined in PSUR089 | 107 | 🟢 ON TRACK | Q3 2026 | 0 | No
| TD089 | PSUR089 | SAGE 1-Step |  |  | 2025-07-01 | [6 empty] | BSI submissiom 28 July 2026, PSUR046, PSUR089, PSUR308 and PSUR309 are combined in PSUR089 | N/A | 🟢 ON TRACK | TBD | 0 | No
| TD089 | PSUR308 | LG Global |  |  | 2025-07-01 | [6 empty] | BSI submissiom 28 July 2026, PSUR046, PSUR089, PSUR308 and PSUR309 are combined in PSUR089 | N/A | 🟢 ON TRACK | TBD | 0 | No
| TD089 | PSUR309 | LG global total LP |  |  | 2025-01-01 | [6 empty] | BSI submissiom 28 July 2026, PSUR046, PSUR089, PSUR308 and PSUR309 are combined in PSUR089 | N/A | 🟢 ON TRACK | TBD | 0 | No
MDR 768184 | TD045 | PSUR045 | ORIGIO® Handling™ | III | Media | 2025-07-01 | 2026-06-30 | 1 year | 2026-08-07 | Not Started | TBD | Combined PSUR | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | 123 | 🟢 ON TRACK | Q3 2026 | 0 | No
| TD045 | PSUR214 | Quinn's Advantage Medium with HEPES | [9 empty] | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | N/A | 🟢 ON TRACK | TBD | 0 | No
| TD045 | PSUR310 | LG global total LP w/ HEPES | [9 empty] | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | N/A | 🟢 ON TRACK | TBD | 0 | No
| TD045 | PSUR311 | LG global w/ HEPES | [9 empty] | BSI submissiom 19 December 2026, PSUR214, PSUR045, PSUR310 and PSUR311 are combined in PSUR045 | N/A | 🟢 ON TRACK | TBD | 0 | No
MDR 768186 | TD117 | PSUR215 | Quinn's Advantage™ Thaw Kit | III | Media | 2024-01-01 | 2025-12-31 | 1 year | 2026-05-04 | In Review | Harish | Combined PSUR | BSI submissiom 18 May 2026, Writed to check to combine 2024 and 2025 | 28 | 🟠 URGENT | Q2 2026 | 0 | No
MDR 768190 | TD053 | PSUR053 | INSORB Skin Stapler and Forceps | III | Medical Device | 2025-05-01 | 2026-04-30 | 1 year | 2026-05-01 | Not Started | Venkata | None | BSI submission on 17 May 2026 | 25 | 🟠 URGENT | Q2 2026 | 0 | No
Formulas:
Days Remaining = IF([Status]="Completed","-",IF(ISNUMBER([Due Date]),[Due Date]-TODAY(),"N/A"))

## Dashboard
📊 PSUR SCHEDULE DASHBOARD — Q1 & Q2 2026
KEY PERFORMANCE INDICATORS
Total PSURs |  | Completed |  | In Progress |  | In Review |  | Not Started |  | Overdue |  | Overall Progress
90 |  | 11 |  | 12 |  | 9 |  | 54 |  | 13 |  | 12.22%
📊 STATUS BREAKDOWN |  |  |  | 👤 WRITER WORKLOAD |  |  |  | 📅 QUARTERLY VIEW
Status | Count | % of Total |  | Writer | Assigned | Completed |  | Quarter | Total | Completed | % Done
Completed | 11 | 12.22% |  | Harish | 16 | 5 |  | Q1 2026 | 21 | 9 | 42.86%
In progress | 12 | 13.33% |  | Jeff | 13 | 2 |  | Q2 2026 | 24 | 0 | 0%
In Review | 9 | 10% |  | Venkata | 15 | 2 |  | Other | 45 | 2 | 4.444%
Assigned | 2 | 2.222% |  | Terence | 14 | 2 |  | TOTAL | 90 | 11 | 12.22%
Not Started | 54 | 60% |  | TOTAL | 58 | 11
TBD | 2 | 2.222%
🎯 DEVICE CLASS BREAKDOWN |  |  |  | ⚡ PRIORITY BREAKDOWN |  |  |  | ⏰ NEXT 30 DAYS - CRITICAL DEADLINES
Class | Count | % of Total |  | Priority | Count | % of Total |  | Metric | Count
Class III | 37 | 41.11% |  | 🔴 OVERDUE | 10 | 11.11% |  | Due in 7 days | 2
Class IIb | 16 | 17.78% |  | 🟠 URGENT | 12 | 13.33% |  | Due in 14 days | 3
Class IIa | 22 | 24.44% |  | 🟡 SOON | 11 | 12.22% |  | Due in 30 days | 6
Class I / Is | 20 | 22.22% |  | 🟢 ON TRACK | 28 | 31.11% |  | Currently Overdue | 13
|  |  |  | ✅ DONE | 11 | 12.22% |  | Avg Days to Deadline | 82
|  |  |  | ⚪ TBD | 18 | 20%
📈 STATUS DISTRIBUTION |  |  |  | 📊 WRITER WORKLOAD |  |  |  | ⚡ PRIORITY DISTRIBUTION
⏱️ Dashboard auto-updates when you change Status, Due Date, or Writer on the 'Maintenance PSURs' and 'BSI PSURs' sheets
Status | Count |  | Writer | Assigned | Completed |  | Priority | Count
Completed | 11 |  | Harish | 16 | 5 |  | OVERDUE | 10
In Progress | 12 |  | Jeff | 13 | 2 |  | URGENT | 12
In Review | 9 |  | Venkata | 15 | 2 |  | SOON | 11
Not Started | 54 |  | Terence | 14 | 2 |  | ON TRACK | 28
TBD | 2 | [5 empty] | DONE | 11
[7 empty] | TBD | 18